| HIGH LIFE HIGHLAND REPORT TO BOARD OF DIRECTORS 2 October 2013 | AGENDA ITEM 13 REPORT No HLH 26/13 |
| --- | --- |

## Quarterly Performance Report - Report by Chief Executive

## Summary The purpose of this report is to present performance information for the period June to September 2013. It is recommended Directors:- - comment on the report and agree that the overall health check on the company for the period is assessed as green; - note the performance of the company against its business plan objectives; and - agree that the operational plans which are contained in the business plan be revised and updated for the December 2013 Board meeting.

| 1. | Business Plan Contribution |
| --- | --- |
| 1.1 | This report supports all the Business Outcomes from the High Life Highland (HLH) Business Plan and will provide an overview of the Company: 1. A positive company image 2. A growing company 3. Delivery of the contract with THC 4. Increased awareness of our products and services 5. Increased customer satisfaction 6. Increased financial sustainability 7. Increased internal collaboration 8. Increased staff satisfaction 9. Safety & environmental compliance |
| 2. | ### Background |
| 2.1 | At the September 2012 meeting Directors agreed that its high level performance monitoring should focus on ten business critical areas. |
| 2.2 | Appendix A contains the summary of performance against the performance indicators. Appendices B to D contain further information. |
| 3. | Summary of performance |
| 3.1 | Seven of the ten indicators have been rated as being on target with three not having been rated as they are annual indicators. |
| 3.2 | The monitoring of the operational plans contained in the Business Plan indicates that most of the actions are either complete or green. At the time that the Board developed the Business Plan, it indicated that the operational plans should be reviewed after a year. It was envisaged that revised operational plans would be considered by the board at its October 2013 meeting, however, it is proposed that these be considered at the December 2013 meeting to allow the results of the board annual review and assessment day held on 23 August and the planning being undertaken by HLH Trading CIC to be built into the new operational plans. |
| 4. | Highland Council Annual Performance and Attitudes Survey 2013 |
| 4.1 | THC has conducted the Highland Council Annual Performance and Attitudes Survey 2013. Appendix D shows the HLH services which are included in the survey in ranked order with THC’s services. Compared with the 2012 survey: - Libraries continue to be ranked second - Other Sports Facilities have dropped from 9th to 13th - Swimming Pools have improved moving from 13th to 12tt - Museums have improved, moving from 15th to 8th - Community Learning/Adult Education has dropped from 20th to 27th |
| 4.2 | While this is a useful track on overall performance, it is difficult to draw too may conclusions from the information as it is quite high level and the performance of other providers could be included in the scores (e.g. museums where HLH is not the only provider). As previously noted by the board, there is work underway to develop a companywide customer survey mechanism which will help to further inform an assessment customer satisfaction levels. |
| 4. | Implications |
| 4.1 | Resource Implications - there are no new resource implications arising from the recommendations of this report. |
| 4.2 | Legal Implications - there are no new legal implications arising from the recommendations of this report. |
| 4.3 | Risk Implications - there are no new risk implications arising from the recommendations of this report. |
| ### Recommendation It is recommended Directors:- - comment on the report and agree that the overall health check on the company for the period is assessed as green; - note the performance of the company against its business plan objectives; and - agree that the operational plans which are contained in the business plan be revised and updated for the December 2013 Board meeting. |  |

Signature:

Designation:	Chief Executive

Date:		20 September 2013

Business Critical Indicators

*RAG

Red 	= No Significant Progress

Amber = Some Slippage

Green = On Target													Appendix A

| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating November 2012 | RAG Rating February 2013 | RAG Rating May 2013 | RAG Rating October 2013 | Summary of Performance: May 2013 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - High level relationship with THC | Annual | Annual meeting, with one of the agenda items to be “assessment of the relationship between HLH and THC”, between: - the HLH chair, vice chair and the chair of the HLH Finance and Audit Committee; and - THC’s Leader and Budget Leader | G | G | - | - | NA – Annual Indicator |
| - Delivery of the SDC with THC | Twice per year | Agreement of THC’s Culture and Leisure Contracts Scrutiny Sub-Committee that HLH has met the terms of the SDC. | G | G | - | G | THC’s ACS Culture and Leisure Contracts Scrutiny Sub-Committee assesses the performance of HLH on a six-monthly basis. At its meeting held on 27 August 2013 it assessed the overall performance of HLH as meeting or exceeding the terms of the SDC. |

| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating Nov 2012 | RAG Rating Feb 2013 | RAG Rating May 2013 | RAG Rating October 2013 | Summary of Performance: May 2013 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Delivery of business plan objectives | Quarterly | Reporting all actions which have been RAG rated red with reasons (and remedial action if appropriate). | G | G | G | G | The overall rating for performance against the business plan has been assessed as being on target. The list of operational plan actions which are red along with explanations/corrective action is in Appendix B. Of the 302 operational plan actions: 0 are recommended for removal 262 are complete or green 41 are amber 2 are red |
| - Financial monitoring | Quarterly | Financial monitoring reports. RAG rating (Red/Amber/Green) definition: - Red = Delivery of SDC over budget - Amber = Delivery of SDC on budget - Green = Delivery of SDC within budget | G | G | G | G | As detailed in the Jun-Sep 2013 finance report, it is confirmed that the Service Delivery Contract has been delivered within budget for the year ended 31 March 2014. |

| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating Nov 2012 | RAG Rating Feb 2013 | RAG Rating May 2013 | RAG Rating October 2013 | Summary of Performance: May 2013 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Health and safety | Annual/ Quarterly | Annual external assessment and report which is agreed by the HLH board. Quarterly review of RIDDOR reportable accidents/incidents. | G | G | G G | G | The H&S Strategic Group continues to meet quarterly and it reviews RIDDOR reports. There are no strategic actions arising from this. Annual report is scheduled for March 2014. |
| - Risk management | Annual | Annual risk report agreed by the HLH board. (The risk register is reviewed quarterly by the finance and audit committee) | G | G | G G | G | The Finance and Audit Committee considered the risk register quarterly. Annual report is scheduled for March 2014. |
| - Leisure centre customer numbers | Quarterly | Comparison graph or trend analysis to the same period in the preceding year(s). | G | G | G | G | Customer numbers at High Life sites have increased over the past 12 months as can be seen in Appendix C. |

| Business Critical Area/PI | Reporting Frequency | Performance Assessment Method | RAG* Rating Nov 2012 | RAG Rating Feb 2013 | RAG Rating May 2013 | RAG Rating October 2013 | Summary of Performance: May 2013 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Quality of service provision | Annual | Annual board report on: Internal assessment of quality: - customer survey for each of the nine areas of work. - review of comments and complaints External assessments of quality e.g.: - THC’s annual public performance survey. - Museum Accreditation (takes place every five years) - The Public Library Quality Improvement Matrix - HMIe inspection of Community Learning and Development | G | G | - | G | Proposed customer feedback system to be developed by December 2013. Analysis of customer feedback to be reported to the HLH board following this. THC has completed its survey “Highland Council Annual Performance and Attitudes Survey 2013” and the table showing net satisfaction rates of HLH services in ranked order with THC services can be seen in Appendix D. |
| - Staff satisfaction | Annual | Annual staff survey and report to the HLH board which includes a year on year comparison of the overall rating of staff satisfaction. | - | - | G | - | NA – Annual Indicator |
| - Value for money | Annual | There are three areas of work which can be benchmarked nationally (and year on year) for value for money by calculating the cost per attendance. These are: Leisure Facilities; Libraries; and Museums. | - | - | G Libraries Others not assessed | - | NA – Annual Indicator |

Operational Plan RAG Rating as at end October 2012											Appendix B

| Service Area | Operational Plan Reference | Red Actions | Target Date (from Operational Plan) | Reason and Corrective Action |
| --- | --- | --- | --- | --- |
| Corporate | - | None | - | NA |
| Adult Learning | - | None | - | NA |
| Archives | - | None | - | NA |
| Arts | - | None | - | NA |
| Leisure Facilities | - | None | - | NA |
| Libraries | LIB 8.3 | Promote Audio books in gym – (listening while exercising) | Mar 2013 | Following completion of the Marketing Plan, libraries staff and Marketing Manager working on an overall marketing plan, working title “Love Libraries”. Target implementation date for campaign – January 2014. |
| Museums | - | None | - | NA |
| Outdoor Learning | - | NA – Operated by THC | - | NA |
| Sport | - | None | - | NA |
| Youth Work | YW 7. | Make available a list of youth work grant funding opportunities for Youth Work organisations in each learning community | Mar 2013 | Absence of a key manager has meant that this has not been progressed. Action due to be completed during the current financial year. |

| Service Areas | Operational Plan Reference | Actions Recommended for Removal by HLH SMT | Target Date (from Operational Plan) | Reason |
| --- | --- | --- | --- | --- |
|  |  | None |  |  |

| Service Areas | Operational Plan Reference | Actions Recommended for Change or Addition by HLH SMT | Target Date | Notes |
| --- | --- | --- | --- | --- |
|  |  | None |  |  |

Appendix C

High Life facilities – High Life card holder user numbers

(Excluding Culloden Academy Community Complex, Averon Leisure Centre or Aviemore Community Centre as inclusion of these facilities would affect the comparative nature of the indicator)

Total user numbers 1st September 2011 – 31st August 2012 = 797715

Total user numbers 1st September 2012 – 31st August 2013 = 880694

Total increase 		                                                     = +11%

Assessed reasons for the 11% increase are as follows:

- 1% - closure of Dingwall Swimming Pool 2011 / reopening of pool & refurbishment of fitness suite 2012

- 1% - Increase in fitness class provision at Lochaber Leisure Centre since refurbishment last quarter of 2011

- 9% - overall increase in fitness programme

Appendix D

Highland Council Annual Performance and Attitudes Survey 2013

Views on our Services: The Net Satisfaction Rate

|  | Service | 2013 % | 2012 % | 2011 % | 2010 % | 2009 % |
| --- | --- | --- | --- | --- | --- | --- |
|  | Payment of Council Tax | 87 | 82 | 82 | 78 | 72 |
|  | Libraries | 84 | 81 | 89 | 78 | 65 |
|  | Walking routes e.g. Great Glen Way | 84 | 80 | 83 | 77 | 56 |
|  | Council Service Points | 79 | 74 | 83 | 74 | 72 |
|  | Refuse/bin collection | 78 | 72 | 73 | 74 | 72 |
|  | Public Parks and other open spaces | 76 | 73 | 82 | 63 | 48 |
|  | Recycling facilities | 75 | 72 | 66 | 61 | 57 |
|  | Museums | 74 | 64 | 79 | 59 | 35 |
|  | Countryside ranger service | 69 | 67 | 71 | 61 | 39 |
|  | Registrars for Births, Deaths & Marriages | 67 | 73 | 80 | 74 | 54 |
|  | Street lighting | 67 | 64 | 69 | 63 | 58 |
|  | Swimming pools | 65 | 64 | 62 | 53 | 40 |
|  | Other sports facilities | 62 | 69 | 72 | 52 | 33 |
|  | Burials and cremations | 61 | 68 | 68 | 63 | 41 |
|  | Secondary education | 60 | 57 | 63 | 60 | 39 |
|  | Primary education | 59 | 65 | 64 | 74 | 49 |
|  | Pre-school services | 58 | 62 | 65 | 63 | 38 |
|  | Environmental Health Service | 54 | 55 | 53 | 33 | 23 |
|  | School meals | 54 | 45 | 60 | 45 | 28 |
|  | Street cleaning | 47 | 43 | 37 | 30 | 30 |
|  | Trading Standards | 46 | 41 | 42 | 38 | 19 |
|  | Cycling paths | 44 | 50 | 65 | 36 | 19 |
|  | Housing information and advice | 43 | 30 | 30 | 18 | 12 |
|  | Services to protect children from harm | 42 | 28 | 37 | 24 | 14 |
|  | School transport | 41 | 33 | 45 | 51 | 31 |
|  | Breakfast and after school clubs | 40 | 24 | 46 | 28 | 7 |
|  | Community learning/adult education | 39 | 47 | 41 | 32 | 20 |
|  | Advice on Benefits | 35 | 30 | 34 | 20 | 18 |
|  | Care at home services | 33 | 23 | 25 | 23 | 14 |
|  | Community Occupational Therapy | 32 | 30 | 28 | 17 | 8 |
|  | Economic development / business support | 31 | 35 | 27 | 10 | 3 |
|  | Services to protect adults at risk from harm | 30 | 28 | 25 | 18 | n/a |
|  | Public conveniences | 28 | 19 | 38 | 18 | 1 |
|  | Gaelic Pre-school services | 27 | 21 | n/a | n/a | n/a |
|  | Dealing with flooding | 27 | 18 | 28 | 21 | 19 |
|  | Residential homes for disabled/elderly people | 24 | 21 | 32 | 11 | 6 |
|  | Pavement maintenance | 21 | 16 | 8 | 6 | 3 |
|  | Planning applications and building warrants | 19 | -2 | 2 | -4 | -3 |
|  | Gaelic Primary education | 14 | 24 | n/a | n/a | n/a |
|  | Winter road maintenance | 14 | 0 | -9 | -23 | -3 |
|  | Planning for future land use (Local Plan) | 14 | 3 | 3 | -9 | -9 |
|  | Gaelic Secondary education | 7 | 14 | n/a | n/a | n/a |
|  | Services to reduce youth offending | 7 | -13 | -9 | -27 | -27 |
|  | Gaelic community learning/adult education | 1 | 15 | n/a | n/a | n/a |

Net satisfaction is calculated by adding the % of respondents who are ‘very’ or ‘fairly satisfied’ and then subtracting from that figure the % of respondents saying they are ‘very’ or ‘fairly dissatisfied’.

In 2009 respondents could have said they were satisfied or not even if they had not used the service.  In 2010 they were given the option to select ‘have not used service’ and from 2011 this option was made clearer along with an alteration to the wording so that it specifies the dates between which people have used the service in order to given an opinion. This change should mean the results of the survey from 2011 onwards are more accurate than ever.